## R&D Items Due_test
Machine | Part Number | QTY | Description | Due Date | Notes | Status | Engineer | UniqueID | 0FBBDA2F35-19CD9328E5
BA-601 REFINER (1999) | 6010000200 | 2 | CASTER STAND, REFINER | 2023-07-25 | In stock as of 4/26 - waiting for Ken to be in KC to issue | Driving | Doug | 0F609C55BB-10B8FD4487
BA-2602 (4039) | 2602080019 | 1 | FTG, TEE, 1/2" JIC | 2023-07-22 | PURCHASE PART | Driving | Dustin | 0B937DEC2C-10B8FD4498
| 2602080020 | 2 | ASSY, TOP SPRAY BAR | 2023-07-22 |  |  | Dustin | 0401ED9192-10B8FD4499
GIB HARVEST (3000) | 64984246 | 20 | TAB,EYE BOLT | 2023-08-09 | NON-STANDARD LASER FOR TESTING SHOWN FOR VISIBILTIY. | Driving | Zac | 0B2496B21C-10B8FD449B
| 95010014 | 20 | EYE BOLT, M8 X 50 |  | PURCHASED ITEM / FOR VISIBILITY |  |  | 169A7CBAE2-10B8FD449C
| 9090202100 | 8 | SHACKLE TURNER | 2023-09-30 |  |  |  | 270079AA50-1590C40C48
| 9090202000 | 200 | ASSY, TURNABLE SHACKLE |  |  |  |  | 12D50155F7-1590C40C48
661(4035) | 6613599332 | 4 | WLDT,TUBE | 2023-07-30 | COMPLETED. ON 5-23, QTY CHANGED FROM 3 TO 4. QTY 1 ON 990013. GLASS BEAD, NOT ACID CLEAN | Driving | Scott | 04519F5395-10B8FD44A2
| 6613500125 | 6 | WLDT,DRIVE BLOCK,WB DRIV | YESTERDAY |  | Driving | Scott | 10E89709B4-10B8FD44A3
| 6613500172 | 6 | WLDT,SCREW BLOCK,FRONT | 2023-08-05 |  | Driving | Scott | 0909326B44-10B8FD44CD
| 93920565 | 40 | RING SHIM 6.35x9.53x0.13 | 2023-08-09 | COMPLETED. PURCHASE - MCMASTER |  | Scott | 07616A7559-10B8FD44CF
| 6613200160 | 40 | SADDLE TURNER | 2023-08-09 | DEMO MACHINE 990013 | Driving | Paul | 0E104755CD-10B8FD44D0
| 6613599160 | 3 | KNIFE,LEFT,EXT,2ANGLE | 2023-08-09 | DEMO MACHINE 990013 | Driving | Paul | 107ADF5964-10B8FD44D2
| 9094966111 | 2 | ASSY, SADDLE DETECTOR | 2023-08-09 | DEMO MACHINE 990013 |  | Paul | 0C7E549CE4-10B8FD44D3
| 6601600025 | 2 | WLDT,LEVER SHAFT | 2023-08-21 | QTY 1 ON DEMO MACHINE 990013 | Driving | Scott | 08E3D2C21A-10B8FD44D7
| 6613600050 | 2 | LEVER | 2023-08-21 | QTY 1 ON DEMO MACHINE 990013 |  | Scott | 0A98BDD161-10B8FD44DA
| 6613399229 | 5 | SUPPORT,GUIDE BAR,SFC | 2023-08-09 | DEMO MACHINE 990013 | Driving | Paul | 06F283A24C-10B8FD44DB
| 6613399183 | 5 | KNIFE GUARD, SFC | 2023-08-09 | IN STOCK. For demo machine | Driving | Paul | 095F01CBFE-10B8FD44DE
1807 (1807-3) | 9025119660 | 1 | ASSY, LIGHT CURTAIN | 2023-11-25 |  | Driving | Zac | 63A77C6501-155528D8C1
| 1807002450 | 2 | ASSY, DRIVE 250 |  |  |  |  | 34EFC50DA6-155528D8EB
| 1807002400 | 2 | ASSY, IDLE 250 | 2023-11-22 |  |  |  | 72942DF673-155528D8F7
| 1807002500 | 2 | 2M MODULE |  |  |  |  | 61D4D3DF32-155528D923
| 1807002700 | 4 | ASSY, 1560 LEGS |  |  |  |  | 62C8256057-17C10DC14A